## Tabelle1
Projectplan Master-Thesis
| Deadline 1 | Deadline 2 | Deadline 3 | Deadline 4 | Deadline 5
When | 2021-04-17 | 2021-05-08 | 2021-05-29 | 2021-06-19 | 2021-06-21
What | Problem Statement 1. Draft & Outline Literature Review | Half the literature review finished | Literature Review Done Draft Version | Methodology finished & Master Thesis Proposal finished | Abgabe Master Thesis Proposal
Questions
| Deadline 6 | Deadline 7 | Deadline 8 | Deadline 9 | Deadline 10 | Deadline 11 | Deadline 12 | Deadline 13 | Deadline 14
When | 2021-07-31 | 2021-08-21 | 2021-09-18 | 2021-10-09 | 2021-10-30 | 2021-11-20 | 2021-12-07 |  | 2021-12-21
What | Suggestion finished | First artefact finished | Second artefact finished | Comparative experiments finished | Documentation of artefacts finished | Documentation of experiments finished | Master Thesis finished for proofreading | Last Review | Abgabe Master Thesis
Questions
Note on A1: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Include Project Plan in Master Thesis Proposal
Note on E5: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Thesis Map, not forgetti as last part of Chapter 1